2019 SERBIA MICS AND 2019 SERBIA ROMA SETTLEMENTS MICS MULTIPLE INDICATOR CLUSTER SURVEY PLAN

June 2019

Contents

1.	Background and Objective	3

2.	Governance Structure	6

3.	Questionnaires	8

4.	Sample Design	21

5.	Survey Instruments	23

6.	Recruitment and Training of Fieldwork Staff	24

7.	Fieldwork	25

8.	Data Processing	26

9.	Data Analysis and Report Writing	28

10.	Archiving and Dissemination	28

11.	Budget	29

12.	Technical Guidance and Support	29

13.	Major Challenges and Support from UNICEF	30

14.	Ethical considerations	30

15.	Timetable	32

Appendix A: Survey Budget	37

Appendix B: Protection Protocol	37

Appendix C: Documents for customisation and review of MICS questionnaires	39

# Background and Objective

Monitoring progress towards the 2030 Agenda for Sustainable Development through MICS

In 2016, the final list of Sustainable Development Goals (SDGs) indicators was endorsed by the UN Statistical Commission, following the global adoption of the 17 SDGs and 169 targets of the 2030 Agenda for Sustainable Development. The final SDG indicator framework includes 230 global indicators, around 30 percent of which are household-based. The MICS questionnaires have undergone rigorous methodological and validation work to broaden the scope of the tools and include new topics that reflect SDG indicators and emerging issues in the 2030 Agenda for Sustainable Development context.

The new topics that have been developed include: rapid water quality testing, social transfers, foundational learning skills (children age 7-14), child and adult functioning, migration status, use of clean fuels and technology, and victimization.

About MICS

The Multiple Indicator Cluster Survey (MICS) is an international household survey programme developed and supported by UNICEF. MICS is designed to collect estimates of key indicators that are used to assess the situation of children and women. Over the past 25 years MICS has evolved to respond to changing data needs, expanding from 28 indicators in the first round to 200 indicators in the current sixth round, and becoming a key source of data on child protection, early childhood education, and a major source of data on child health and nutrition. In addition to being a data collection tool to generate data for monitoring the progress towards national goals and global commitments aimed at promoting the welfare of children, MICS has provided valuable data for MDG monitoring, being a major source of data for the UN Secretary General’s Final Millennium Development Goals Progress Report.

Since the inception of MICS in the 1990s, close to 300 surveys have been carried out in more than 100 countries. As part of the global effort to further develop national capacities to generate and analyse high quality and disaggregated data, UNICEF launched the sixth round of MICS surveys in October 2016, with results expected to be available starting from the early 2018. Today, MICS is well positioned to play a central role in the new 2030 Agenda for Sustainable Development data landscape alongside other key demographic, health and socio-economic surveys and to complement data from administrative sources and censuses. MICS was already covering some of the SDG indicators that are household-based. After undergoing rigorous methodological and validation work to broaden the scope of the tools and include new topics that reflect SDG indicators and emerging issues in the 2030 Agenda for Sustainable Development context, MICS6 questionnaires in the sixth round will cover about 40 percent of household-based SDG indicators.

As governments begin to develop national frameworks to monitor progress towards the SDGs and establish baselines, strategic planning and investments will be required to collect robust, more frequent, and timely data. The new round of MICS presents a unique opportunity to support this process.

Situational analysis - Serbia

Serbia is an upper-middle income country that has made significant progress on a wide-ranging reform agenda. Studies, evaluations and research carried out over the past years particularly in the areas of health, reform of social services, and education show that much progress has been made towards achieving Serbia’s national Millennium Development Goals, particularly in the areas of health, reform of social services, and education. The prospect of EU integration is driving the comprehensive reforms of the economic and social sectors. Serbia became a candidate for European Union (EU) membership in 2012, and started the negotiations for membership in January 2014. The EU Strategy for the Western Balkans launched in February 2017 sets out a roadmap for EU enlargement of the Western Balkans countries with 2025 given as the date for potential accession by Serbia.

Over the past 5 years, the country has continued to revise its normative framework and has strengthened a number of institutions to enforce accountability and guarantee respect for rights and the full implementation of the legal framework, without discrimination.

A reversal in trends of the unemployment rate in Serbia started in 2013, as after years of economic crisis, less people were out of the job market. In 2016 employment in Serbia has increased by 5.6 percent and while in 2017 an increase in employment was retained, although it was at a slower pace compared to the year before as it has increased by 2.8 percent. The employment rate in 2017 was 46.7%. The overall unemployment rate in 2017 has decreased to 13.5 percent, which relative to 2016, represents a 1.8 drop in percentage points (p. p.). Young people are still most affected by unemployment, the rate being 31.9 percent in 2017, which is lesser than the previous year by 3.0 p.p..

In 2016, the percentage of the total population living in absolute poverty was 7.3. Children below the age of 14 were disproportionately impacted and their poverty rate was higher compared to the overall population, amounting to 8.4 percent for the same period. Likewise, households with six members or more and those with lower education levels were particularly badly affected, with poverty rates of 12.1 and 19 percent respectively. Poverty is marked by significant regional variations and disparities among population groups, with the Roma being the most vulnerable. An estimated 50 percent of Roma households live below the poverty line. Conditions for children in the southern part of the country lag behind in terms of absolute poverty rate compared to the more developed north (13 in Southeast Serbia to 4 in Belgrade), and rural areas fare considerably worse than urban ones (5.1 in urban areas compared to 10.5 in rural ones). Poverty is a multi-dimensional phenomenon, and other indicators of well-being reveal continuing disparities of vulnerable groups.

Secondary analysis of MICS data showed that as much as 74% of the population in Roma settlements would fall in the poorest 20% of the general population.

The 2014 Serbia MICS and 2014 Serbia Roma Settlements MICS showed that while there has been significant progress over the past four years in almost all indicators of Roma child status, the equity gap when compared to the general population remains. This is evident, for example, when it comes to infant and child mortality rates (12.8 and 14.4 among children from Roma settlements versus 5.7 and 6.6 in the general population), preschool participation (6 percent versus 50 per cent among the general population), and secondary school enrolment (22 per cent versus 89 per cent for the general population).

The most important reform processes related to children and supported by UNICEF in Serbia are in the areas of child protection, education and health. In the area of child protection, the main focus is on the prevention of family separation through strengthening of support to biological families, development of community-based services and strengthening of social protection programs. In the area of education, efforts are made to fully implement legal provisions for inclusive education, enabling equal access and the right to quality education for all children. The main focus in the area of health is support to ECD services and Roma health.

Data for policy design and monitoring

Serbia is one of the few countries in which all five previous rounds of MICS were implemented. It was however in three different states. The first MICS was conducted in 1996 while Serbia was a part of the Federal Republic of Yugoslavia to review progress towards the World Summit for Children with the follow up MICS2 conducted in 2000. MICS3 came in time to show progress in the meeting “A World Fit for Children Declaration” but also in the implementation of the National Plan of Action for Children (NPA) and the Poverty Reduction Strategy of Serbia. Serbia was then part of the State Union of Serbia and Montenegro which ceased to exist in 2006 when Serbia became independent. The MICS3, MICS4 and MICS5 implemented included Roma samples as well, to close the data gap for this very vulnerable population group.

As a result of the availability of reliable, internationally comparable and disaggregated data, major international and national policies and strategies have been developed and their implementation monitored based on MICS data. Many of these key policies would rely on the data from MICS6.

MICS6 data are required to support monitoring of progress in reaching the Sustainable Development Goals, monitoring of implementation of the Roma Inclusion Strategy and Action plan, as well as other social inclusion related policies in areas of health, education and social protection. They are particularly important for the monitoring and reporting on the progress achieved on the EU accession path (monitoring of the Action Plan for the Chapter 23, Sector budget support indicators).

# Governance Structure

Memorandum of Understanding

A Memorandum of Understanding (MoU) was signed between the Statistical Office of the Republic of Serbia (SORS) as Implementing agency and the UNICEF Serbia Country Office in February 2018 with a goal to execute the project "Multiple Indicator Cluster Survey (MICS)”. The MoU clearly defines main responsibilities for both parties in agreement as well as the ways to resolve any problems during the implementation. MoU is part of this document as Appendix D1.

As the implementation of MICS6 will be undertaken in partnership with UNFPA, a separate MoU was signed between UNFPA, SORS and UNICEF in April 2018 with responsibilities of all partners clearly specified. This MoU is also submitted as Appendix D2.

Implementing agency

MICS6 will be implemented by the SORS. SORS will take the lead in all phases of planning and realization of the survey through its representatives in the Steering Committee, Technical Committee and the internal SORS Survey Team. Besides that, the specific tasks to be performed by SORS staff are:

- Preparation of survey tools, customization of questionnaires, preparation of methodological guidelines for survey implementation;

- Organizing the training for the listing of all existing buildings, objects, dwellings, households, number of children under 5 living in the household, and selection of survey samples;

- Organising and conducting the first training for pre-test, conducting pre-test and developing pre-test report;

- Customization and testing of the CAPI applications

- Organizing and conducting the main training for all fieldwork staff, conducting the PAPI and CAPI field practice and the pilot;

- Organising field work; coordination of work of all teams in the field; interviewing of the households; field monitoring and supervision over fieldwork teams;

- Data collection and secondary editing;

- Data processing and analysis;

- Preparation of the Survey Findings Report and thematic snapshots;

SORS MICS Team

The SORS has established a special team of their staff that will provide expertise in different phases of the survey. Namely:

- Survey Coordinator –Ms Nadezda Bogdanovic

- Fieldwork Coordinator - Ms Dragana Djokovic-Papic

- Sample expert – Ms Mirjana Ogrizovic- Brasanac

- Data processing experts –Mr Vladica Jankovic, Ms Tatjana Zaric and Mr Nedjeljko Calasan

Additional technical experts from the fields of health, education and child protection will be hired on a consultancy basis for the purposes of fieldwork training, data analysis and preparation of the Survey Findings Report and Thematic Snapshots..

The Survey Coordinator will serve as a focal point for ethical considerations arising during field work. Formal review and endorsement of the questionnaires and tools for 2019 Serbia MICS and 2019 Serbia Roma Settlements MICS will be performed by HML in the role of an external Ethics Review Board.

UNICEF MICS Team

UNICEF MICS Team has its members at the country level, regional level as well as at the global level. At the country level the team consists of the UNICEF Child Rights Monitoring Specialist – Ana Prodanovic and the MICS Consultant – Filip Mitrovic, who will be providing daily support and work in close collaboration with the Statistical Office team engaged on MICS6.

The regional MICS team consists of the regional MICS Coordinator -Eduard Bonet Porqueras and UNICEF regional consultants in three main areas: Household Survey Implementation – Ana Abdelbasit, Sampling - Sinan Turkyilmaz and Data Processing – Tijana Sukilovic. The regional team shall provide on-going on-site and off-site technical assistance to the Project to support and oversee implementation of sampling, training, pre-testing, fieldwork, data processing and analysis, report writing in accordance with envisioned MICS steps and methodology.

UNICEF global team will provide technical guidance and ensure alignment with global methodology.

Steering bodies

The Survey Steering Committee, consisting of representatives of the Ministry of Labour, Employment, Veteran and Social Affairs, Ministry of Education, Science and Technological Development, Cabinet of the Minister without portfolio responsible for demography and population policy, Ministry of Construction, Transport and Infrastructure, Republic Institute for Social Protection, Ministry of Health, Institute of Public Health of Serbia, Ministry for European Integration, Office of Human and Minority Rights, Social Inclusion and Poverty Reduction Unit of the Deputy Prime Minister (SIPRU), Statistical Office of the Republic of Serbia, Delegation of the European Union to the Republic of Serbia, UNFPA and UNICEF, will be responsible for the overall organisation, coordination and management of the survey. It will be responsible for the final survey design, follow-up of survey implementation and defining and follow-up of survey findings. The responsibilities of the Steering Committee will also include overall endorsement of MICS6, approval of final survey instruments, support in promotion of MISC6 in public and among local authorities, endorsement and dissemination of the Survey Findings Report.

In addition to this, a Technical Committee is established of experts from the Institute of Public Health of Serbia, ministries responsible for health, education and social policy, demography, human and minority rights, construction, EU integration, SIPRU, SORS, EU Delegation, UNFPA and UNICEF. The main responsibilities of this committee are to participate in technical discussion in relation to the methodology, to customise and approve final questionnaires, review and discuss preliminary findings and the draft report and closely monitor all phases of the survey implementation.

# Questionnaires

MICS will include four questionnaires; for the household, for women 15-49 years of age, for children age 5-17 years and for children under age five.

A separate “Questionnaire Form for Vaccination Records at Health Facility” will be administered as children’s immunizations records are kept in health facilities.

SORS possess geocoded enumeration areas for the entire Republic of Serbia. They are geocoded in the official coordinate system of the Republic of Serbia and are available in shape file format. The shape files are the property of the Republic geodetic authority of Serbia, while SORS is the user of the shape files. Because geocoded data exists for all EAs, further geocoding will not be needed for 2019 Serbia MICS and 2019 Serbia Roma Settlements MICS Serbia.

The following modules will be included in the 2019 Serbia and 2019 Serbia Roma Settlements MICS:

Household Questionnaire:

| Household Information Panel List of Household Members Education [3+] Employment* Household Characteristics | Material deprivation** Social Transfers - Attitudes toward children with disabilities* - Household Energy Use - Water and Sanitation |
| --- | --- |

Questionnaire for Individual Women:

| - Woman’s Information Panel - Woman’s Background - Fertility - Desire for Last Birth - Maternal and New-born Health - Contraception - Unmet Need | - Attitudes toward Domestic Violence - Victimisation - Marriage/Union - Informed decision on reproductive health care* - Sexual Behaviour - Life satisfaction |
| --- | --- |

Questionnaire for Children Age 5-17 Years:

| - 5-17 Child Information Panel - 5-17 Child’s Background - Child Labour - Child Discipline [5-14] | - Child Functioning - Parental Involvement [7-14] |
| --- | --- |

Questionnaire for Children Under Five:

| - Under-Five Child Information Panel - Under-Five’s Background - Birth Registration - Birth Grant* - Early Childhood Development - Child Discipline [1-4] | - Child Functioning [2-4] - Breastfeeding and Dietary Intake [0-2] - Immunisation [0-2] - Anthropometry |
| --- | --- |

The Questionnaire Form for Vaccination Records at Health Facility will be used to collect immunization records for children under three years of age.

Indicator list and background information are attached as Appendices to Country Survey Plan.

Country specific modules added:

Household questionnaire

Attendance to compulsory preparatory preschool program (PPP) – country specific module

- Set of questions on attendance to PPP (Preschool Preparatory Program) are introduced to collect data on attendance rates to PPP (ED22), facilities available for PPP (ED24.), modes of commuting to PPP (ED25) availability of such programs in terms of geographic proximity (ED26) and in case of non – attendance the reasons for not having children in PPP (ED28[A-E])

- Justification and stakeholders: Preparatory Pre-school program (PPP) was introduced in the Serbian education system in the school year 2006/2007 as a part of regular compulsory education. It has a specific prescribed program and lasts 9 months (as a school year). The module has been developed on the basis of LSMS questionnaire used in Serbia in 2007 in cooperation with and upon request of the Ministry of Education. It was tested and introduced in MICS4 and MICS5 questionnaires and has provided required data. As disaggregated administrative data still don’t exist, the request was repeated for this data to be provided through MICS6.

Reasons for non-attendance of early learning and development programs – country specific module

The set of questions was introduced in MICS4 to explore reasons for non-attendance of preschool education programs. It revealed that beside the issue of cost and capacity, parents’ opinions on the importance and value of preschool education presented the main barrier for higher attendance rates. MICS4 and MICS5 data revealed that majority of parents see preschool mainly through its caretaking role, failing to recognize its potential value for child development. In addition to that, data revealed different types of reasons and barriers characteristic for different groups of children and parents. This data was widely used by all relevant stakeholders and a request to collect them again was repeated by the Ministry of Education. Set of questions was further modified for MICS6 to reflect reasons for non-attendance specific for PPP and not kindergarten attendance.

Employment status (EMP] – country specific module

- Set of questions on employment will be introduced in MICS6 to explore the employment status of household members 15 years of age and above. No upper age limit is set for this module, as is the case with labour force survey implemented by SORS. Questions also include structure of unemployed and employed population and whether employment was achieved through engagement in formal or informal sector (EMP6, EMP7 and EMP8). At the same time, data on types of benefits generated through employment will be collected (EMP9.)

- Justification and stakeholders: EMP module was requested by SIPRU team and EU Delegation in Serbia to provide data on employment status, primarily among Roma population.  Information on employment status of the general population is available through Labour Force Survey but it doesn’t provide data disaggregated by ethnic status.

Material deprivation (MD] – region specific module

- An additional set of questions, material deprivation (MD) module was also added to the household survey (MD1 to MD14 questions).

- Justification and stakeholders: module was suggested by UNICEF RO not to reproduce indicators already available in SILC but to use the MD indicators as disaggregation variables. Some SILC indicators may however be used to compare the status of the Roma population against the general population. Another purpose of the MD module, is to refine the wealth index variable used in MICS6 as one of the key disaggregation variables. Insight from already collected MICS data will be enriched through adding data on material and housing deprivation. Data on material and housing deprivation are especially important in Serbia as a country with a relatively high share of the population at risk of poverty. As data in MICS6 will also be collected for Roma communities in Serbia it will provide insight into the levels of deprivation faced by this community.

Attitudes toward children with disabilities – country specific module

- Set of questions in module on attitudes toward children with intellectual and physical disabilities (AC2C), impact of children with disabilities (CwD) on work in school (AC2D), life achievement expectations of CwD (AC2E).

- Justification and stakeholders: The focus on full inclusion of children with disability is an important aspect of the reform processes in Serbia and the supporting UNICEF country program. Although legal changes have been put in place a few years back, small scale surveys and Monitoring Results for Equity System (MoRES) analysis done through focus groups indicated that attitudes towards children with disability create serious obstacles in overcoming their exclusion.

- An opinion poll conducted in 2009 and other related research revealed a high percentage of the population with negative attitudes towards inclusion of children with disabilities and their right to family environment and inclusive education. Negative attitudes of the general public and professionals present one of the major obstacles in more effective inclusion of children with disability. There were also quite different attitudes towards children with motor/physical disability and children with intellectual impairments so therefore 2 groups of questions were included. The main legislative framework for inclusive education was introduced during 2010 but it was reinforced in the period until today and a lot of efforts were introduced to address obstacles to full inclusion of all children. It is therefore important to assess whether social norms which were recognised as one of the key obstacles changed in the period from the last MICS. This data was widely used by all relevant stakeholders and a request to collect them again was repeated by the Ministry of Education.

Individual Women’s Questionnaire

Informed decision on reproductive care [ID] – country specific module

- Informed decision on reproductive health care (ID) module adds questions on voluntarily of intermarital sexual intercourse, decisions about health care and reproductive care and contraception.

- Justification and stakeholders: UNFPA requested addition of the questions necessary to generate SDG indicator 5.6.1, so these questions will also be included (ID1, ID2, ID3, ID4, ID5, ID6A and ID6B). This module is based on global level consultations between UNICEF and UNFPA so that standardised version of the module will be included in MICS upon standardisation and harmonisation.

Under-Five Questionnaire:

Birth grant [BG] - country specific module

- Birth Grant (BG) Module was introduced to assess coverage and up-take of this universal social protection benefit. Questions are related to awareness of the birth grant (BG0), applications for birth grants (BG1), receiving birth grants (BG2) and reasons for not applying for birth grant (BG3).

- Justification and stakeholders: Birth grant is one of the family/child related benefits and like for the other family/child related benefits, previous surveys showed high non-take up among the poor due to the lack of information on the benefits and complicated administrative procedures.  The module was introduced in MICS5 and provided data that influenced legislative changes. This module is essentially a part of the Social Transfers module but since this universal grant is targeting every new born, up to a maximum of four children per family it logically fits to U5 questionnaire. Due to legal changes from 2017 amounts of the benefit are significantly increased and it is important to assess impact of the new provisions on take-up and coverage. The module was requested by the Technical committee members and supported by the Steering committee.

Country specific questions were added in particular MICS modules:

Within the Household Questionnaire:

Education [ED] Module - country specific questions

- Question about starting first grade of primary school (ED18) is auxiliary question (variable) that is necessary for calculating whether all children of the appropriate age attend the appropriate class as children in Serbia can start primary education with 6 or 7 years of age. Question about type of school attended (ED11) will provide answers that will look at types of private schools attended

Household characteristics [HC] Module – RO suggested questions on material deprivation

- Set of questions on material deprivation was added to the household characteristics module (HC2A, HC3A, HC7A, HC9A, HC9A1, HC9C, HC9C1, HC9ZA, HC9ZB, HC9ZB1, HC10E, HC10E1, HC11A1, HC11B, HC12A1, HC14A, HC14B, HC14C, HC14D, HC20).

Social transfers [ST] Module - country specific questions

- Set of questions in social transfers module (ST9-ST17) was added to assess applications for, coverage and reasons for not applying for Financial social assistance and Child allowance as the key social protection benefits for the poorest.

- Justification and stakeholders: Serbia has good administrative data collection systems that provide data on the number of beneficiaries of different cash benefits. However, earlier surveys (LSMS 2007) showed high non-take up of the child related benefits among the poor due to the lack of information on the benefits and complicated administrative procedures. The country specific module was developed and introduced in MICS5 and provided valuable disaggregated data on take-up and targeting with the main cash benefit programs. Since the Social Transfers module became a standard MICS module, Serbia will only add customized questions related to uptake and reasons for non-uptake of the financial social allowance and child allowance (for every child in the HH). Questions related to the uptake with the birth grant will be like in the case of MICS 5 included in the U5 questionnaire as they related to children 0-4 years old. Data generated with this module in MICS5 provided important guidance for the policy revision of child allowances and birth grant that was introduced in 2017 and enabled analysis of the impact of child related benefits on particular outcomes for children. Legal revisions of another cash program (Family social allowance) are expected in 2019 and MICS data should contribute to it. This customization was requested by the Technical Committee members and supported by the Steering Committee.

Within the Individual Women Questionnaire:

Woman’s Background[WB] – country specific questions

- Set of questions was added (WB14A, WB14B, WB14C, WB14D, WB14E, WB14F, WB14G) related to the current employment status, status within the last 12 months, ways and means of seeking employment, status related to formal or informal employment and benefits that women receive from their employment status. As some of these questions are the same as questions from the EMP module within the Household Questionnaire: a filter questions will be added to skip them in those cases when the Household Questionnaire was administered to the same respondent avoiding asking the respondent the same questions.

- Justification and stakeholders: Women overall are a group within active labour force that has a significantly higher unemployment rate compared to the overall population. This is especially the case for women within Roma community. More in depth data on women as participants in the labour force will allow for more targeted activities of stakeholder and policy makers. Questions in this module will provide not only data on employment status but also on means and methods unemployed women from both overall and Roma population are utilising to actively seek employment. Questions related to benefits will provide data on the share of employed women who have access to different types of benefits based on employment. These data will also enable insights into correlations between mother’s employment status and child outcomes. Employment module was developed based on the request from SIPRU team and EU delegation in Serbia and the questions were repeated within the women’s questionnaire to ensure quality data.

Fertility [CM] Module - region specific questions

- Set of questions on abortion added, including issues related to lifetime experience of abortion, miscarriages and stillbirth (CM19, CM20, CM21A, CM21B, CM22, CM23, CM24, CM25, CM26, CM27, CM28, CM29, CM30, CM31, CM32 and CM33).

- After CAPI test additional questions (CM18A. and CM18B.) related to whether a birth was a twin birth or single birth was added to CM module. Reason for this addition are related to weight of a child at birth and how twin births affect this indicator.

- Justification and stakeholders: In Serbia in 2016 over 15,500 abortions were reported. This figure only accounts for abortions performed in public health care facilities, putting the country among the leading countries in Europe in terms of prevalence of abortions. Research has shown that about 16,000 adolescent pregnancies were registered every year in Serbia, and more than 90 percent of them are unplanned and unwanted and end with abortion, which is a major risk for reproductive health. Many adolescents opt to perform a secret abortion, which carries an even higher risk - both for reproductive health and for their lives and remains unrecorded making the official data on abortion rate highly unreliable. The questions were included on suggestion of Technical Committee, Steering Committee and the Ministry of Health in MICS5 and provided quality data. The request to include these questions again came from UNFPA and was supported by the TC and SC. Additional question introduced in MICS6 relates to a number of abortions in the last 12 months and last 5 years. This was requested by the Institute of Public Health to allow for validation of administrative data. The module was updated based on the suggestions from UNICEF RO to include assurance of privacy, introduction to the topic of abortions, a question on total number of abortions as an anchor question and checks of total numbers.

Maternal and Newborn Health [MN] Module - country specific questions

- Set of questions was added related to home visits by patronage nurses (MN6A, MN41, MN42), coverage with programs of pre-natal counselling (MN6B, MN6C, MN6D), question regarding presence of the child in the room with mother after birth (MN40).

- Justification and stakeholders: The questions MN6A, MN6B, MN6C, MN6D, (MN4C and MN4D in MICS5 and MN27B and MN27A in MICS 4) were tested and introduced in MICS 4 and MICS 5 questionnaires and provided required data on this important aspect of health care envisioned by the prescribed package of health care but difficult to monitor through administrative data. Questions related to Baby-friendly programs were required by the Ministry of Health. All questions were discussed and suggested for inclusion formally by the Technical Committee, the Steering Committee and the Ministry of Health and the Institute of Public Health.

Contraception [CP] Module - country specific questions

- Set of question related to familiarity with methods to delay or avoid pregnancy (CP0) was added in MICS 5. In MICS6 questions on reasons for stopping (CP3A) and never using (CP3B) methods to delay or avoid pregnancy were added. In MICS6 an additional question on medical consultations has been included (CP4A).

- Justification and stakeholders: It was recognised that if interviewees are not familiarised with different methods which are by the MICS methodology considered as ways to avoid or delay pregnancy that some of the methods are underreported (withdrawal in particular). Therefore, as of the MICS4, the interviewers are familiarised with the methods and then asked if they use it. Thanks to this adaptation, reporting of withdrawal as a contraception method grew from 14% in MICS3 to 32% in MICS4 and 35% in MICS5. This adaptation was in 2013 requested by, Ministry of Health, Ministry of Education and Ministry of Youth and Sport and now supported by the Technical Committee and Steering Committee. UNFPA requested addition of the questions related to reasons for stopping or never using methods to delay or avoid pregnancy and consultations with medical professionals.

Unmet Need [UN] module - country specific questions

- Set of questions on ideal number of children were added (UN5A and UN7A)

- Justification and stakeholders: based on request from UNFPA questions added aim to determine what desired number of children for interviewed women would be. Such data is necessary for further shaping population policy in the country. Current efforts of the government to alleviate low birth rates are focused on changes in policy which is significantly increasing birth grant value for every new-born child. Measure intends to mitigate financial constraints women might feel in making a decision to expand their family. However, there is no collected data on actual desired number of children women desire, to determine what is the desired size of the family from women’s perspective.

Attitudes toward Domestic Violence [DV] Module - country specific question

- A question on knowing where to report cases of domestic violence was added (DV2) as per request of the Office for Human and Minority Rights that is a member of the Technical and Steering committees. During pre-testing, additional question (DV3) was also added to collect data on institutions to which women would report cases of domestic violence to.

Within the Under-Five Questionnaire:

Under-five’s Background [UB] Module - country specific questions

- A set of questions added related to preschool facilities that child attends and reasons for non-attendance (UB8C and UB8D are added which were already used in MICS5 as EC6A and EC6B). UB8D question was further modified for MICS6, to account for possible reasons for non-attendance specific to kindergarten and not PPP as well.

- Justification and stakeholders: The questions UB8C and UB8D were tested and introduced in MICS4 and MICS5 questionnaires and provided required data – data on types of preschool facilities are needed by the Ministry of Education as the administrative data systems are not effective in collecting data from private providers and NGOs. Further, data on reasons for non-attendance of preschool are key in further development of preschool education policies and support measures.

- A set of two additional responses were added to EC5 question to collect more data on activities in which household members engaged in one or more household activities with children ages 2 to 4 years.

Under-five’s Early Childhood Development [EC] Module - country specific responses

- Two additional responses were added to question EC5A (EC5A[A] and EC5A[B]) to collect additional data on activities household members have engaged with children ages 1 to 4 years old.

- Justification and stakeholders: World Bank is interested in additional data about parental behaviours to support their ECE project. These additional activities were added in the EC5A question, even though they are not solely concentrated on the support for learning to minimise further interventions to the Under-Five Questionnaire.

Immunisation [IM] Module – country specific questions

- Questions IM21A - IM21H were added to IM module to check for vaccines child received if it did not receive a pentavalent vaccine for four times. Question IM21D checks if child received all polio vaccines to check for full polio immunization.

Within 5-17 questionnaire:

Parental Involvement [PR] Module - country specific questions

- A set of questions added to PR module to parental involvement module assistance child is getting for homework (PR6A), participation in paid activities (PR6B), attendance in free school activities (PR6D), existence of Parental Council (PR7A), familiarity with decisions of Parental Council (PR8A), sessions of Parental Council (PR9A).

- Justification and stakeholders: Questions on assistance in homework, participation in paid activities and activities in school (PR6A and PR6B) were added on request of the Ministry of Education, Science and Technological Development. Data collected will provide insight on what is the additional burden on children in terms of achieving homework requirements on one side and whether they are supported by adults in these activities, and on the other how many and which parents have to pay to enable children to participate in out of school activities. Question PR6D will provide insight on participation rates in school based activities. In strategic documents Ministry cites very high number of private tutoring lessons children attend to for various reasons, either to catch up on regular school curriculum or to prepare for academic competitions. However, Ministry does not have any concrete data in this area and adding these questions will quantify those activities. Questions on activities of Parental Council in schools were adopted from original MICS6 regarding governing bodies in school (PR7A, PR8A and PR9A). In national school system, only one parent per class of students in each school is selected as a member of Parental Council, a school governing board. Expected answers on membership are very small, so questions were adopted to reflect level of knowledge of activities of Parental Council.

The following questionnaires and modules from the global standard MICS questionnaires will be excluded from the 2016 Serbia MICS:

Household Questionnaire:

| Insecticide Treated Nets | During 2016, according to IPH Batut only 24 cases of imported cases of malaria were detected in Serbia with incidence of 0.33/100,000 |
| --- | --- |
| Hand washing | Previous MICS have shown very high levels for this indicator |
| Salt Iodization | Based on the Law on Standardisation all salt for consumption must be iodized IPH Batut issued a report on National Survey of the Biological Impact of Universal Salt Iodisation in the Population of Serbia results suggesting that Serbia has eliminated endemic goitre. |
| Water quality | Based on legislation (the Law on Water) all potable water must be regularly inspected . IPH Batut issues annual reports on health requirements of potable water from public waterworks. Report is based on water quality testing data performed by regional institutes of public health. |

Questionnaire for Individual Women:

| Mass Media and ICT | Data are available from annual survey on Usage of information and communication technologies in the Republic of Serbia, SORS |
| --- | --- |
| Birth History | Fertility module is used |
| Post-Natal Health Checks | 100% deliveries happen in hospitals where mother and child care including post-natal health checks are part of a routine service. Institute of Public Health of Serbia is the main source of administrative statistics in health Data available from data collected by Ministry of Health, IPH Batut |
| Female Genital Mutilation | NA |
| HIV/AIDS | Data will become available through the National Health Survey to be implemented in Autumn 2019 |
| Adult Functioning | Data will be available from the National Health Survey to be implemented in Autumn 2019 |
| Maternal Mortality | Data available from SORS Vital statistics and annual SORS data |
| Tobacco and Alcohol Use | Data will become available through the National Health Survey to be implemented in Autumn 2019 |

Questionnaire for children age 5-17:

| Foundational learning skills | MoESTD did not prioritize collecting data through Foundational learning skills module. Ministry representatives find data available from Trends in International Mathematics and Science Study (TIMSS) by Institute for Educational Research and Programme for International Student Assessment (PISA), by OECD that will be carried out during 2018 in Serbia as sufficient for their needs. |
| --- | --- |

Questionnaire for Children under Five:

| Care of Illness | Data are available from administrative sources (IPH Batut). |
| --- | --- |

The questions that are excluded are:

Within the Household Questionnaire:

- HL module: question on recording of men, as individual men questionnaire is not used in MICS6 in Serbia (HL9)

- HC module: question related to the mother/native language of the head of household (HC1B).

Data are available from Population Census data.

- WS9, WS.10 - not relevant (1% of general population and 2% of population from Roma Settlements was using unimproved sources of water)

Within the Individual Women Questionnaire:

- MN module: questions related to immunization of the mother (MN7, MN8, MN9, MN10, MN11, MN12, MN13, MN14, MN15, MN16, MN17 and MN18).

Questions not applicable as adult women are not immunised according to national regulations.  and not relevant to Serbia as there are no cases of neonatal tetanus or malaria as per IPH Batut Report on Communicable Diseases. MN module: questions related to delivery in health facility (MN27, MN28, MN29, MN30 and MN31). Data not relevant to country specific context as more than 99.5 percent of deliveries are handled in health facilities

- MA module: questions related to other wives and partners are excluded (MA3 and MA4). Data not relevant to country specific context.

Within the Questionnaire for Children age 5-17:

- PR module: questions related to teacher absence (PR13, PR14 and PR15) - not relevant to country specific context, as under the Law on Elementary Education and Law on Secondary Education teacher strikes are allowed only if there is a minimum of hours classes are held, making it mandatory to hold at least 30 minutes of each class during strikes. Also, any classes that were missed due to any of the reasons (teacher absence or strike) must be held on a later date.

Within the Under-Five Questionnaire:

- IM module: question about the time of receiving the first polio vaccine (IM17, IM18 and IM19), question related to Yellow Fever vaccination (IM27) and questions about participating in campaigns related to immunization and child health days (IM8 and IM12) and questions on rotavirus vaccination (IM24 and IM25). Questions were excluded as not applicable as Yellow Fever and rotavirus vaccines are not included in the recommended vaccination calendar and no immunisation campaigns were implemented since MICS5.

MICS questionnaires will be translated into Serbian and additional modules/questions will be included in translated versions. Once the questionnaires are set up they will be back-translated into English and sent to UNICEF Regional Office for review. SORS will work on translations as well as on design of national questions together with UNICEF Serbian office.

Upon receipt of comments from UNICEF regional and global teams, all instruments, including paper questionnaires and methodological instructions and manuals (except the Manual for Anthropometry) will be tested during pre-test. The main aim of the pre-test is to test the questionnaires-understanding of questions, adequacy of response categories, questionnaire flow, instructions for interviewers. Pre-test training will be organised in one of the pre-selected locations (Zrenjanin, Belgrade or Ub, pending on the availability of sample selection due to ongoing SORS activities) from December 9th to December 18th 2018. Initially, training was planned for the period from November 18th to November 27th, but it was postponed for three weeks, to allow for additional time to work on questionnaires. It lasted 10 days and will include 3 days for pre-test fieldwork. Anthropometry will not be trained and tested during the pre-test. Trainers were 6 staff employed in the Statistical Office of the Republic of Serbia and four of them are responsible for four questionnaires.

The training was attended by 11 interviewers (potential supervisors). There was one team member per team representing 11 MICS6 teams. Pre-test was done using PAPI test in order to have interviewers fully familiarized with the MICS methodology and data collection on paper.

MICS5 Survey Pre-test, SORS, Serbia

For the general population pre-test of the MICS6 questionnaires, 100 households were selected and 50 households for Roma population. Questionnaires for households, women, children under 5 and children between 5 to 17 will be used during pre-test. Selected households for the pre-test will be excluded from sample of 400 clusters for 2019 Serbia MICS and 100 clusters to be sampled for 2019 Serbia Roma Settlements MICS.

Results of the pre-test were used to further modify, customize, and finalize the questionnaires, and the questions that are found to be unclear were revised and reformulated for the final versions. Pre-test results were compiled in Pre-test report and sent to UNICEF.

Once the questionnaires were finalized, the CAPI test was organized to test the application. The CAPI testing aimed to have same interviewers involved that conducted the pre-test questionnaire as participants for the CAPI test. In this situation, they did not need to receive methodological training in full, but only training on the use of the CAPI application, before conducting CAPI test fieldwork.  Out of 11 interviewers participating in pre-test training, 10 of them returned for the CAPI testing.

CAPI test training was organised in a Ub, from February 18 to February 27, 2019. It lasted 10 days and included three days for CAPI test fieldwork. For the CAPI testing of the MICS6 questionnaires 110 households were selected. Sample size proposed for CAPI testing was smaller relative to pre-test as main goals is to test the application itself, rather than quality of the questions. As with pre-test, selected households will be also excluded from samples for 2019 Serbia MICS and 2019 Serbia Roma Settlements MICS. CAPI test results were compiled in CAPI report and sent to UNICEF.

# Sample Design

The primary objective of the sample design for the Serbia Multiple Indicator Cluster Survey is to produce statistically reliable estimates of most indicators, at national level, for urban and rural areas, and for the four regions of the country: Belgrade, Vojvodina, Sumadija and Western Serbia and Southern and Eastern Serbia.

In order to assess disparities confirmed during the previous waves of the MICS surveys and to provide national estimates, two samples will be created. One sample will be defined as a representative of the general population of Serbia (refer to Serbia sample) and the second one, for the Roma settlements, representative of the population living in Roma settlements.

A stratified, two-stage random sampling approach will be adopted, for the selection of the survey samples.

Sample sizes for Serbia and Roma settlements sample in MICS6, were calculated as 8000 households (400 enumeration areas (EA)) for Serbia sample, and as 2000 households (100 EA) for Roma settlements sample.

Serbia is characterized by a very low fertility rate and average number of household members. For example, one generation of born children makes less than 1% of population, and an average number of household members is around 3. The birth rate and average household size among Roma living in Roma settlements is slightly higher than in other population groups. Overall, sample size for Roma settlements is 2000 households, without stratification at second stage. To determine sample size requirements following indicators were used: Overweight prevalence; unmet need among women and currently using contraceptive method among women 15-49 in union.

Table1. Sample size for MICS6

|  | No. of households in sample | Expected No. of Households | Expected No. of women 15-49 | Expected No. of children under 5 in the sample | Expected No. of children 5-17 years | No. of clusters in sample |
| --- | --- | --- | --- | --- | --- | --- |
| Serbia sample | 8,000 | 6,720 | 4,772 | 2,306 | 1,847 | 400 |
| Roma living in Roma settlements | 2,000 | 1,760 | 1,740 | 835 | 486 | 100 |
| Total | 10,000 | 8,480 | 6,512 | 3,141 | 2,333 | 500 |

The sample design methodology can be summarized in the following table:

| Target population: | Households, children under 5 years, children 5-17 years, women aged 15-49 years, and other household members depending on modules which will be included in the survey. |
| --- | --- |
| Subpopulations: | The general population of Serbia and Roma population living in Roma settlements. |
| Sample frame: | The MICS sample will be built up on the bases of the Population Census conducted in 2011. Since the sample frame is 7 years old, after the selection of enumeration areas, updating of the list of households must be done, prior to the selection of households. Teams who will do the listing will visit each enumeration area, enumerate all existing buildings, objects, dwellings and households, and ask for the actual number of children under 5 living in the household. |
| Type of sample: | The sample will be based on two-stage stratified random sampling design. Primary sampling units will be enumeration districts, and then the second stage sampling units will be households. |
| Stratification: | Enumeration district will be stratified according to territory at the NUTS2 level (four regions) for the both samples and the type of the settlement (urban, other), and after listing, in the case of the Serbia Sample, according to type of households (with children under 5, without children under 5). |
| Allocation of the sample: | Allocations of the samples will be based on the pending expert report. |
| Sample selection scheme: | At the first stage, enumeration districts will be selected with probabilities proportional to the size of population (number of households), and at the second stage, households will be selected with equal probabilities. |
| Interviewing technique: | Directly in dwelling unit – face to face and anthropometric measurement of children under 5. |
| Listing | Listing will be done in paper form, from January 15th until February 19th. A four-day training for the listing will be conducted from January 9th till 12th January 2019, based on the listing guidelines provided by UNICEF RO. Training is planned for 55 participants, implemented by 5 SORS staff. Number of participants for listing training is 55 (20 enumerators, 20 mappers, 10 supervisors and 5 reserves) |

# Survey Instruments

It is estimated that boards, scales, laptops with accessories will be needed in the indicated amounts:

Measuring boards: 9 packs

Portable baby/child length/height measuring board, made of wood, 2 boards packed in a carton box (9 boxes). Portable baby/child length-height measuring board is used to measure: a) recumbent length of a baby up to 24 months old. b) Height of a child aged 24 months and up in vertical position. Smallest graduation: 0.1 cm. Measurement range: 0-120 cm. UNICEF Supply Catalogue; S0114530. Stock item. Price* for set of 2: USD 164.

- Scales: 17 pieces

Electronic scale for weighing adults and children, 150kg x 100g (17 boxes). The Scales have measuring range 0 to approximate 150 kg. Minimum graduation: 100 g. They are with tarring button, so called "mother-and-child" function. UNICEF Supply Catalogue; S0141021. Stock item. Price* ea. USD 129.

- 80 Laptops for CAPI

The laptops will be provided by SORS. The laptops will come with bag, mouse and charger. Laptops will be Notebook Acer Aspire ES1-332 with one 64-bit processor with four cores per processor; they will have 4 GB DDR 3 RAM memory; hard drive with 500 GB capacity; in terms of interfaces - one USB 2.0, USB 3.0, one HDMI; with the screen size of 13,3” and picture resolution, 1366x768; all laptops will feature MS Windows 10 OS; a battery with 3-cells and both Ethernet 100/1000 and wireless LAN 802.11 connectivity. All laptops will have Bluetooth 3.0 connectivity. Out of 80 laptops provided by SORS, 55 will be allocated to the fieldwork teams, with additional 11 laptops allocated to fieldwork teams as extra laptops available throughout fieldwork in case there is a need to replace laptops being used in the field while 14 will be used in the central office.

# Recruitment and Training of Fieldwork Staff

The public call for fieldwork staff will be advertise in a daily newspaper with national circulation, on SORS website, National Employment Service website and on the online job portal – https://www.lakodoposla.com.  Fieldwork coordinators received written criteria for the selection of the team members and were asked to provide names of persons and some other characteristics that meet the following requirements: sex depending to the status in the team, at least secondary education, driving license, able to establish rapport for child measuring, their availability to attend the main training in full, be present in the field for the entire duration of fieldwork etc. Supervisors are also required to be present during the entire duration of fieldwork.

- Timing of training – Right before the fieldwork. Initially fieldwork was planned between April to June 2019. However due to issues with securing timely receival of a grant covering expenses of main fieldwork training and fieldwork itself, decision was made to postpone these activities for the second half of 2019. Adjusted dates envision main fieldwork to last between September 2nd and November 10th 2019.

- Length of training – Twenty three days (03-25 August 2019). During the Fieldwork Training, 2 days will be used for PAPI fieldwork exercise, 3 days for CAPI pilot survey and 2 and a half days for resting.

- Methodology and content of training – Content of training is in accordance with MICS6 methodology. Agenda is in the phase of the preparation.

- Profiles of trainers – Trainers will be SORS statisticians and experts for specific topics like anthropometry, immunization, cash benefits etc. Some of trainers have prior MICS experience.

- How training will be organized – Centralized location for training with a plan for conducting a field practice for using paper questionnaires and later on during the training a CAPI field practice using laptops and a 3-days pilot study to simulate fieldwork in full. By the end of the main training, there will be some separate parts dedicated to measurers and supervisors. The training will be delivered in the forms of plenary presentations, workshops and sessions for practical exercising. A group trained through the pre-test training will be used as additional resources during practical work sessions.

A training package, based on the customised MICS manuals, will be prepared by the internal SORS MICS Team, including written instructions like Manual for interviewers, Manual for supervisors and Manual for Anthropometry.

The fieldwork will be conducted by 11 teams, 8 for the national and 3 teams for the Roma sample.

The field work teams will have 6 members of the following composition:

- National Sample Frame will have 8 teams of the following structure:

| 1 supervisor | (8 in total) |
| --- | --- |
| 4 interviewers | (32 in total) |
| 1 measurer | (8 in total) |

Interviewers and a supervisor should be females, while a measurer can be male or female according to the manual.

Interviewers in both cases (for national and Roma sample) will be female and will conduct interviews for the household, women, one randomly selected child age 5-17 and U5 questionnaire. It is recommended that all team members covering Roma sample be Roma, however in some cases, it might not be a possibility, like for the roles of supervisors. Therefore at least interviewers for the Roma sample should be Roma.

- Roma sample frame will have 3 teams of the following structure:

| 1 supervisor | (3 in total) |
| --- | --- |
| 4 interviewers | (12 in total) |
| 1 measurer | (3 in total) |

One person more per team should be recruited as reserve team member and will participate in the training for the fieldwork together with the interviewers, supervisors and measurers (to take into account drop-out). Interviewers will be without previous experience with MICS surveys.

# Fieldwork

The fieldwork is planned to be conducted within 13 weeks during September, October and November 2019. Each team will have 2 cars for the transportation of the team members, laptops for CAPI, survey material and equipment for anthropometry. Given that a fewer number of teams, especially Roma teams will need to visit the EA’s across the territory of the Republic of Serbia, those teams will have longer travel times. That is the reason why these teams will be provided with accommodation e.g. lodging for a night during the fieldwork.

- Having in mind the timing for Key findings is planned for 6 months after all post fieldwork activities at the latest, it is necessary that the fieldwork ends no later than November 2019.

- Data collection will be monitored by coordinators regularly throughout the duration of fieldwork in order to provide feedback, with the highest intensity at the very beginning of the field work in order to spot common mistakes and provide guidance and support to solve it. Survey methodologists/coordinators from SORS and the UNICEF MICS Coordinators will conduct monitoring. The aim of the monitoring is to provide recommendations for improvement and to continuously monitor the fieldwork. Monitoring phase should be done throughout the fieldwork and should be most intensive at the beginning and at the end of fieldwork.

- Parallel with this, data entry will be realised during the fieldwork. Data entry will take place in the households using laptops and will be transferred via Bluetooth connection to supervisors, and after getting back from the fieldwork, MICS supervisors will be required to send the data to the database in central office using internet connection. In this way preparation and usage of field check tables will help in spotting the mistakes and make dynamics of the fieldwork more efficient.

- Calculation of fieldwork duration and the number of teams was done on the basis of the following assumptions:

National population sample

- - Sample =8000 HH

- - Number of clusters – 400

- - Duration of field work – 13 weeks

- - Number of days spent by team in each cluster - 1.3 day

- - Number of clusters covered by 1 team in one week – 3.9 clusters

- - Number of clusters covered by 1 team in 13 weeks – 50

- - Number of clusters/number of clusters per one team= 400/50 = 8 = 8 teams needed

The above estimates include time required to collect data from primary health care facilities which will be done by 1 team member

Roma population sample

- - Sample =2000 HH

- - Number of clusters – 100

- - Duration of field work – 10 weeks

- - Number of days spent by team in each cluster - 2 days

- - Number of clusters covered by 1 team in one week – 3.33 clusters

- - Number of clusters covered by 1 team in 10 weeks – 33

- - Number of clusters/number of clusters per one team= 100/33 = 3= 3 teams needed

The above estimates include time required to collect data from primary health care facilities which will be done by 1 team member

The Survey Coordinator will serve as a focal point for ethical considerations arising during field work.

# Data Processing

The Census and Survey Processing System (CSPro) software package will be used for data entry. UNICEF MICS Team will provide the CSPro software to the SORS, at or before the MICS Data Processing Workshop. The customised global MICS6 CAPI application, with user interface translated into Serbian language, will be used during fieldwork, i.e. the CAPI test and main fieldwork.

Data collection will be performed with CAPI method, on PC laptops, by 44 female interviewers, 11 measurers and 11 supervisors. Use of laptops will facilitate a number of tasks on controlling and supervising the team performance in fields, including:

Provide interviewers tasks to record observations on households;

Obtain collected data from the interviewers;

Check household questionnaires and individual questionnaires;

Complete work on the cluster;

Prepare data files for sending to the central office.

Measures will be taken to ensure both electronic and physical safety of collected data. Supervisors will send data to the central office headquarters using the Internet File Streaming System (IFSS), an encrypted cloud-based electronic file delivery system. Data will be protected by firewall software packages on servers. The primary objective is to deliver files from one user (Automated client application) to another (Control center client application) in an exceptionally fast and secure way. Safe storage and transport of the laptops during fieldwork is also a challenge. To mitigate this challenge, the interviewers will travel in teams and will be able to support each other in protecting the equipment. Team members will be trained to lock their laptops during meal and rest times. Additional concern in terms of physical security of laptops is protection against atmospheric conditions and for this purpose procurement of laptop accessories is planned, equipping each team with spare battery, case, screen protector, spare stylus, SD card and vehicle charger.

Testing of the CAPI application was conducted after finalization of questionnaires and “in-house” validation of data entry app. In-house validation means a simulation of CAPI process in SORS.

CAPI application field testing was conducted in February 2019, after paper-based testing and finalizing of the questionnaires in December 2018. The CAPI testing lasted ten days (09-17 February 2019), conducted using revised and reviewed questionnaires. Three days were planned for fieldwork, in order to test the application, instructions and CAPI process. It covered about 100 households.

The results from the test of the CAPI application were compiled in a report, and used to finalize the application. The key purpose during the CAPI testing is early identification of potential problems with the equipment and any weaknesses in CAPI components, such as data entry applications, file management system, data transmission, distribution of households between interviewers, data transmission to the central office, applications for monitoring and control of field operations used by the central office.

During the whole process of data collection and processing, the procedures and standard programs developed in the framework of the global program MICS6 and adapted to the 2019 Serbia MICS and 2019 Serbia Roma Settlements MICS questionnaires will be used.

Data processing (that includes e.g. structure checks and secondary editing of data received from the teams, generation of data quality tables, drafting tabulation plan tables) will begin simultaneously with the data collection, in September 2019, and will end early in March-April 2020, nearly two-three months after the fieldwork completion. This work will be done under close supervision of UNICEF RO and HQ MICS teams, with respective reviews of datasets, syntaxes, household and individual weights and household well-being indices.

The Statistical Software Package for Social Sciences (SPSS) will be used for the analysis. UNICEF headquarters will provide the licensed copy of this software to the SORS. With this aim, the standard syntaxes and tabulation plans developed by UNICEF will be adapted and used.

Cover of Executive Summary Report for MICS5, UNICEF Serbia.

hild friendly reports) if available.]

# Data Analysis and Report Writing

The empty shell tables will be drafted by end of 2019.

Preliminary Summary Findings Report will be prepared in line with the standard format provided by HQ. The preliminary report will be discussed by the Technical Committee of the survey and presented to the Steering Committee. Suggestions for revision will be taken into account in order to produce Survey Findings Report of the survey in May 2020. The task force consisting of experts from different research fields will be established for data analysis and preparation of the Thematic Snapshots, after Survey Findings Report is published.

# Archiving and Dissemination

The SPSS data and survey documents will be archived using the IHSN Micro data Management Toolkit. The toolkit (a software package) and training on how to use it will be provided by UNICEF during the MICS Data Processing Workshop.

The Survey Findings Report , once endorsed by the Steering Committee will be printed in 300 copies in English and 350 in Serbian language, and will be widely distributed through the government and networks of civil society organizations.

While 2019 Serbia MICS and 2019 Serbia Roma Settlements MICS survey is ongoing, the Survey archive will be updated accordingly. Upon completion, the final survey archive will be available online and will have all the key survey documents (questionnaires, MoU, sampling documents, training material etc.), final syntaxes and tabulation plans, datasets and reports. The datasets will be available to end users after they register online.

In addition to the Survey Findings Report, MICS indicators will be available to end users in DevInfo Serbia database and in the online global MICS Tabulator that UNICEF plans to release by the end of 2020.

# Budget

The detailed budget calculations are presented in the Appendix A.

# Technical Guidance and Support

The main guidance for MICS is available at http://mics.unicef.org. The survey team, with relevant experts in each case, will attend the three MICS workshops, focused on survey design, data processing and data interpretation, further analysis and dissemination, that will be organized by the UNICEF Regional Office and UNICEF New York MICS Team. In addition to the templates, standards and guideline documents provided at childinfo.org, many completed MICS surveys will also serve as examples.

Technical support, which includes online support and in-country visits, will be provided by the UNICEF Regional Office (through the regional MICS Coordinator and the experts to be mobilized by the Regional Office) and by UNICEF New York MICS Team as described in the MICS Technical Assistance Framework presentation delivered at the Survey Design Workshop and in the Appendix to the MoU on Technical Collaboration.

The main guidance for MICS is available at http://mics.unicef.org The survey team, with relevant experts in each case, will attend the three MICS workshops, focused on survey design, data processing and data dissemination and further analysis, that will be organized by the UNICEF Regional Office and UNICEF New York MICS Team. In addition to the templates, standards and guideline documents provided at http://mics.unicef.org, many completed MICS surveys will also serve as examples.

Technical support, which includes online support and in-country visits, will be provided by the UNICEF Regional Office (through the regional MICS Coordinator and the experts to be mobilized by the Regional Office) and by UNICEF New York MICS Team as described in the MICS Technical Assistance Framework presentation delivered at the Survey Design Workshop and in the Appendix to the MoU on Technical Collaboration.

The SORS will also be supported by the Child Rights Monitoring Specialist as the UNICEF MICS Focal Point in Serbia and a full time UNICEF MICS Consultant employed by UNICEF Serbia.

Technical support from the UNICEF Regional Office will be particularly valuable in the critical points of the survey - verification of customised questionnaires, listing, sample design, data processing and data quality review as well as during the final data analysis.

Additional technical support will be provided to the SORS in the phase of data analysis and report writing.

# Major Challenges and Support from UNICEF

Financial support is crucial for the planning of 2019 Serbia MICS and 2019 Serbia Roma Settlements MICS. Funds were allocated by UNICEF HQ (250,000 USD) and UNFPA (115,000 USD), and additional funds (350,000 EUR) are expected to be collected through IPA 2018.

Initial plan of activities envisioned that 22 days of main fieldwork training would start in March 2019, while fieldwork was planned for the period between April and Jun 2019. It was planned that financing for these activities would come from IPA 2018 Programme. However, due to gaps between time necessary to implement public procurement process for services of hotel accommodation for the main fieldwork training and call for MICS interviewers on one side and signing of IPA 2018 agreements on the other, issue of eligible expenditures for SORS arose. Having this in mind, SORS was compelled to temporarily suspend activities related to main fieldwork training and fieldwork itself.

On March 21, 2019, Financial Agreement between European Commission and Republic of Serbia was approved by the Government of Serbia, which will enable financing of the annual Action IPA Programme for 2018. As signing of the Agreement is imminent, SORS and UNICEF have concluded that it is optimal to postpone start of the main fieldwork training to a period between August 3 and August 25, 2019, while main fieldwork would last from September 2 to November 10, 2019.

# Ethical considerations

The research process, data collection, and reporting will respect ethical standards in research when human subjects are involved as follows:

- The participants will be included in the survey on a voluntary basis, following informed consent where they will be informed about the purpose of the survey, the lead agency, the average length of the questionnaire and the right to withdraw

- All data that is collected will be anonymized before publishing survey findings and only aggregated data will be presented. Personally identifiable information will be used to access households during the listing and the households will then be coded so that survey responses are not linked to personal data.

- Geo-tagging data (GPS coordinates of households) will be utilized for geo-spatial analysis of survey findings and will be linked to cluster numbers and not individual households

- Throughout the research, confidentiality will be maintained in the following ways:

  - Interviewers and survey managers will be trained on the importance of and practical steps towards maintaining confidentiality

  - Survey supervision will include the aspect of interviewers adhering to privacy and confidentiality standards

  - Data will be handled only by the MICS survey team and all necessary precautions will be taken to prohibit access to third parties (e.g. through password protection of technical equipment etc.)

  - The data collected through CAPI will be transmitted through a secure, encrypted connection and to servers that are secured from external access

- The privacy of all participants will be respected through adequate arrangements during the survey (e.g. by proposing a setup where the interviewer and the respondent will not be in hearing distance of other adults, or children old enough to understand the interview proposing to postpone sensitive questions till the required privacy conditions have been met etc.)

- To mitigate the potential risk of emotional harm to participants (e.g. through questions in the module of victimization), interviewers will have at hand the contact numbers of counselling services that the respondents can contact, should they wish to do so. Individual cases of emotional disturbance will be reported to the survey manager.

- In instances where risks actually occur, they will be noted and collected by supervisors at the end of field work discussions. These will be submitted to the survey manager who will in turn discuss them with the ethics focal point within the MICS team/Steering Committee.

2019 Serbia MICS and 2019 Serbia Roma Settlements underwent the Ethical Board Review (ERB). Initial application for approval was submitted on January 31st with   first request for feedback received back from ERB on February 5th.  Final approval by ERB for the project was received on March 5 2019.  MICS team submitted proposed questionnaires, instructions for interviewers and additional documentation to provide assurances that ethical considerations will be integrated in the survey implementation.

# Timetable

| 2018 |  |  |  |  |  |  |  |  |  |  |  |  |  | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tasks |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1-3 |
| PLANNING AND LOGISTICS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data-gap assessment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare and sign the MoU* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Survey Design Workshop | In 2017 | I |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare the Survey Plan and Budget*, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify survey team and national MICS consultant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Establish steering and technical committees |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Select personnel for listing operation, pre-test of questionnaires and test of CAPI application, main fieldwork and SORS data processing staff working on syntax |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Order supplies: tablets and accessories, scales, boards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Carry out logistical arrangements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| QUESTIONNAIRE DESIGN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Customise questionnaires and manuals (including translation and back translation of questionnaires and translation of manuals, if needed)* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Training and pre-test of questionnaires in paper format |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare report from pre-test of questionnaires; finalise questionnaires and manuals* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SAMPLING AND LISTING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare sample design and design weights* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare listing materials and prepare staff for training and listing operation* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct listing training and pilot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct listing operation (including listing clusters for the PAPI and CAPI field exercise and pilot study); prepare listing report* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Carry out sample selection* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Enter sample data (if listing was done using paper forms) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare the sample for the fieldwork CAPI application* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DATA PROCESSING PROGRAMMES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data Processing Workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Customisation of CAPI application* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Training and fieldwork test of CAPI application |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare report from test of CAPI application; finalise CAPI application* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FIELD STAFF TRAINING AND FIELDWORK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Train fieldwork personnel and conduct a pilot study |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect data in the field |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1-3 |
|  |  | 2018 |  |  |  |  |  |  |  |  |  |  |  | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |

|  | 2018 | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tasks |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| DATA ENTRY & PROCESSING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data entry, secondary editing and data cleaning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare survey weights* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Finalise datasets* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DATA ANALYSIS AND TABULATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Customise Tabulation Plan* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Customise SPSS syntaxes* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Populate Tabulation Plan* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data Interpretation and Dissemination Workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TBD |  |  |  |  |
| REPORT WRITING AND DISSEMINATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare Survey Findings Report * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Plan and prepare dissemination materials* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Disseminate Survey Findings Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Narrative Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ARCHIVING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collate documents/materials for survey archive* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare survey archive |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
|  | 2018 | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  |

## Appendix A: Survey Budget

## Appendix B: Protection Protocol

2019 Serbia MICS

Multiple Indicator Cluster Survey

Protection Protocol

The following is a table of the potential risks and management strategies to be put in place by implementing Statistical Office of Republic of Serbia.

| Risk | Risk Management Strategy | Responsibility |
| --- | --- | --- |
| Participant has grave and obvious health concerns (particularly signs of inflicted violence). | Steering committee determines a standard for when action needs to be taken and referral pathways. Interviewers to provide details of relevant local facilities, services and procedures to participants as needed. | Steering committee – ethics focal point Interviewers |
| Communities or participants have complaints or concerns about the survey | Establish complaints focal point from implementing partner to addressing issue. In the first instance, concerns will, if possible be addressed by interviewers and supervisors, then the survey manager. Information to be provided to participants and communities regarding contact details of concerns or complaints focal point. | Interviewers/ Supervisors/ Survey manager |
| Disclosure of events that conflict with local laws. Where no Legislation exists | No measures will be taken unless the respondent asks for help in which case the interviewers will provide information on relevant support services/help lines (determined in advance and provided to interviewers as a list of local or relevant health and social support services that are available and willing to provide support as necessary). | Interviewers Supervisors Country Focal Point Relevant government and service providers Interviewers |
| Respondent becomes visibly distressed by certain questions | If necessary, interviewer asks participant if they want to stop for a few minutes and return to it later. A second option may be to ask the respondent if he/she wants to skip the particular question. If respondent continues to be distressed, interviewer may stop the interview and make plans for a return visit if the respondent agrees. | Interviewers |
| Limited or no privacy (e.g. an adult in direct proximity) | Interviewers can ask for a place in the home where they and the respondents will not be in hearing distance of any adults If privacy is limited before certain parts of the questionnaire, interviewers may explain the nature of questions and again, ask for privacy. Finally, the interviewers may return to these questions at a later time when there is more privacy. | Interviewers |
| Data on respondents are shared (breach of confidentiality) | Survey manager discusses individual cases with the field teams. Re-training on confidentiality may be necessary. Identified data (data identifying location and names of respondents) are kept in a password protected file. Data are anonymised before sharing of data (as per usual MICS procedures). Further mitigation measures will be decided on a case-by-case basis in consultation with ethics focal point. | Survey Manager |
| Interviewers know respondents. | The supervisor assigns a different interviewer to the household | Survey Manager |
| Interviewer’s beliefs in conflict with that of the community. | Interviewers are trained not to provide any information regarding their religious or political affiliations or other beliefs. | Survey Manager |

Risks in the Field

In instances where risks actually occur, it is important that they be noted and collected by supervisors at the end of field work discussions. These should be noted by supervisors and submitted to the survey manager.

## Appendix C: Documents for customisation and review of MICS questionnaires

|  | List of MICS6 indicators, as well as any survey-specific indicators, that are expected to be calculated based on the customised questionnaires | ☒ |
| --- | --- | --- |
|  | Information on the education system in the country: education laws/regulations that describe levels and grades/years of the national education system, as well as information on any changes to the system that may affect data collection and analysis | ☒ |
|  | Table/map showing correspondence between the ISCED 2011 classification of education and the national education system classification (levels and grades/years) | ☒ |
|  | Showcard(s) that will be used for testing literacy at modules WB and MWB Showcards should be produced in all written languages that are commonly used, regardless of whether questionnaires in these languages are being used or not. | ☒ |
|  | Documentation on the providers of antenatal and postnatal care in the country This can be an assessment or a large document, but should enable the team to identify response categories for questions that include providers of such services. | ☒ |
|  | Information on the birth registration system in the country: brief overview of legislative requirements, information on length of validity of birth certificates (are certificates valid for a limited time-period, e.g. six months, or are they permanent), is a certificate free of charge at the time of registration, does issuance at a later date require payment of a fee, etc. | ☒ |
|  | Vaccination schedule that is used in the country (or schedules if there has been a change during the last three years) | ☒ |
|  | Information on any national immunization day campaigns that took place in the last three years | ☐ |
|  | Scanned copies of vaccination cards that have been filled in, preferably from different regions/districts of the country (the date of birth of the child should be visible if possible, all other personal details should be blacked out) | ☒ |
|  | A document/regulation that outlines or lists the government recommended homemade fluids for treatment of diarrhoea. | ☐ |

Statistical Office of the Republic of Serbia http://www.stat.gov.rs, June 2018

Statistical Office of the Republic of Serbia and UNICEF. 2014. Serbia Multiple Indicator Cluster Survey and Serbia Roma

Settlements Multiple Indicator Cluster Survey, 2014, Final Reports. Belgrade, Serbia: Statistical Office of the Republic of

Serbia and UNICEF.

Child poverty in Serbia: The analysis of Multiple Indicator Cluster Survey data, available at: https://www.unicef.org/serbia/en/reports/child-poverty-serbia

For one randomly selected child in each household. This questionnaire is administered to the mother or caretaker. In rare cases when a child age 15-17 has no mother or caretaker identified in the household, the respondent will be the child him/herself.

Administered to their mothers or caretakers.

*refers to Serbia specific nationally developed modules

** refers to region specific module

* refers to Serbia specific nationally developed modules

Health Statistical Yearbook of Republic of Serbia 2016

Ministry of Education, Science and Technological Development, Education Development Strategy 2020 http://www.mpn.gov.rs/wp-content/uploads/2015/08/STRATEGIJA-OBRAZOVANJA.pdf

Report on Communicable Diseases in Serbia for 2016, IPH Batut

National Survey of the Biological Impact of Universal Salt Iodisation in the Population of Serbia, 2007, IPH Batut, available at http://kan-kaz.org/english/files/salt_iodisation_serbia2007.pdf

Report on Health Requirements for Potable Water from Public Pipelines in Serbia for 2016, IPH Batut

For PAPI surveys: Data Entry and Data Processing

In country discussions and a data-gap analysis should be conducted prior to taking the decision on whether to conduct a MICS.

Timelines for MICS workshops can specified following confirmation by UNICEF RO and HQ.

Serbia team representative attended Survey Design Workshop in Tbilisi in February 2017

An asterisk * indicates items that include reviews by UNICEF RO and HQ.